## Defect Tracking Log
Project Name: SoftwareTestingMaterial
Defect ID | Defect Description | Created On | Created By | Severity | Priority | Status | Assigned Date | Assigned To | Resolution | Resolution Date | Estimated Time To Fix | Actual Time To Fix | Root Cause
DEF-2026-001 | Admin Property Edit - Property update with valid data fails to save changes correctly | 2026-06-01 | Ahmed Ossama | High | P1 | Inprogress | 2026-06-01 | Developer 1 |  |  | 8 hours
DEF-2026-002 | Admin Property Edit - Empty title validation not working; allows saving property without title | 2026-06-01 | Ahmed Ossama | Medium | P2 | Inprogress | 2026-06-01 | Developer 2 |  |  | 4 hours
DEF-2026-003 | Admin Property Status - Property status change operation fails; status not updating in database | 2026-06-01 | Ahmed Ossama | High | P1 | Inprogress | 2026-07-01 | Developer 3 |  |  | 6 hours
DEF-2026-004 | Admin Filter Edit - Filter edit modal throws error on save; unable to update filter configurations | 2026-06-01 | Ahmed Ossama | High | P1 | Inprogress | 2026-07-01 | Developer 4 |  |  | 8 hours
DEF-2026-005 | Admin Filter Delete - Filter deletion operation encounters error; filters not being removed from system | 2026-06-01 | Ahmed Ossama | High | P1 | Inprogress | 2026-07-01 | Developer 1 |  |  | 6 hours
DEF-2026-006 | Admin Filter Cancel - Cancel delete filter operation throws error; modal not closing properly | 2026-06-01 | Ahmed Ossama | Medium | P2 | Inprogress | 2026-08-01 | Developer 2 |  |  | 3 hours
DEF-2026-007 | Admin Filter Toggle - Toggle filter status encounters error; active/inactive state not changing | 2026-07-01 | Ahmed Ossama | Medium | P2 | Inprogress | 2026-08-01 | Developer 3 |  |  | 4 hours
DEF-2026-008 | Agent Details View - Agent detail page fails to display complete agent information correctly | 2026-07-01 | Ahmed Amr | Medium | P2 | Inprogress | 2026-08-01 | Developer 4 |  |  | 5 hours
DEF-2026-009 | Auth Reset Password - Invalid token error handling fails; user not receiving proper error message | 2026-07-01 | Ahmed Sherif | High | P1 | Inprogress | 2026-08-01 | Developer 1 |  |  | 6 hours
DEF-2026-010 | Auth Reset Password - Password reset with valid token completely broken; users cannot reset passwords | 2026-07-01 | Ahmed Sherif | Critical | P0 | Inprogress | 2026-07-01 | Developer 2 |  |  | 12 hours
DEF-2026-011 | Auth Register - User role not persisting after registration; defaults to wrong role on login | 2026-07-01 | Ahmed Sherif | Medium | P2 | Inprogress | 2026-08-01 | Developer 3 |  |  | 5 hours
DEF-2026-012 | Auth Register - Maximum password length validation not enforced; allows passwords exceeding limit | 2026-08-01 | Ahmed Sherif | Low | P3 | Inprogress | 2026-09-01 | Developer 4 |  |  | 2 hours
DEF-2026-013 | Auth Register - Weak password validation bypassed; system accepting passwords below strength requirements | 2026-08-01 | Ahmed Sherif | Medium | P2 | Inprogress | 2026-09-01 | Developer 1 |  |  | 4 hours
DEF-2026-014 | Auth Login - Back button after login redirects to login page instead of preventing navigation | 2026-08-01 | Ahmed Sherif | Low | P3 | Inprogress | 2026-09-01 | Developer 2 |  |  | 3 hours
DEF-2026-015 | Auth Login - User session not persisting correctly; users logged out unexpectedly after page refresh | 2026-08-01 | Ahmed Sherif | High | P1 | Inprogress | 2026-08-01 | Developer 3 |  |  | 8 hours
DEF-2026-016 | Auth Forgot Password - Password reset email not being sent to valid email addresses | 2026-08-01 | Ahmed Sherif | High | P1 | Inprogress | 2026-08-01 | Developer 4 |  |  | 6 hours
DEF-2026-017 | Developer Properties - Get project by invalid ID fails to return proper error response | 2026-08-01 | Youssef Ahmed | Medium | P2 | Inprogress | 2026-09-01 | Developer 1 |  |  | 4 hours
DEF-2026-018 | Developer Properties - Project update with valid data fails; changes not saved to database | 2026-08-01 | Youssef Ahmed | High | P1 | Inprogress | 2026-09-01 | Developer 2 |  |  | 7 hours
DEF-2026-019 | Developer Properties - Notification not triggered when new project is created by developer | 2026-09-01 | Youssef Mohamed | Medium | P2 | Inprogress | 2026-09-01 | Developer 3 |  |  | 5 hours
DEF-2026-020 | Developer Properties - Active project count not updating correctly after project creation | 2026-09-01 | Youssef Ahmed | Low | P3 | Inprogress | 2026-09-01 | Developer 4 |  |  | 3 hours
DEF-2026-021 | Developer Properties - Developer count not incrementing after new developer signup | 2026-09-01 | Youssef Ahmed | Low | P3 | Inprogress | 2026-09-01 | Developer 1 |  |  | 3 hours
DEF-2026-022 | Developer Properties - Delete developer property operation encounters error; property not removed | 2026-09-01 | Youssef Ahmed | High | P1 | Inprogress | 2026-09-01 | Developer 2 |  |  | 6 hours
Note on G4: Raj: Choose from the dropdown list
Note on H4: Raj: Choose from the dropdown list