## Cover
General Information
Project ID
Client
Author(s)
Creation Date
Modification Date
Privacy Information
It contains information of a sensitive nature. This information should not be given to persons other than those who are involved with this project or who will become involved during its lifecycle.
Change Control
Revision Date | Author | Section(s) | Summary

## STATUS REPORT
Overall progress of the QA cycle(on time/delayed/stopped) | On time
Total number of test cases | 142
Number of testers | 6
Test cycle duration (in days) | 1.5
Status of 09/01/2026
Number of test cases planned | 142
Number of test cases executed | 142
Number of test cases executed overall | 142
Number of defects encountered today | 22
Number of defect encountered so far | 22
Number of critical defects- still open | 1
Overall Status
Number of test cases planned | 142
Number of test cases executed | 142
Pass Percentage of the defects | 84.51%
Defects density (per day) | 5.5
Critical defects percentage | 4.55%